## Sheet1
Project Co-ordinator:- Prof.Uzmamasrat Shaikh. Project Guide:- Prof.Manjusha Tatiya. Name of Team Members:-1] Deepak Bohara(22113) 2] Abhinav Maindre (22101) 3] Vishwajeet Birajdar (22238) 4] Vikas Dain(22239)
Project Evaluation Sheet Topic:- Real time Chat
Sr.no. | Meeting Points discussed with Guide | Start Date | End Date | Responsible Members | Remark
1 | BrainStorming for the ideas with guide and members | 2021-02-12 | 2021-02-15 | All the Team Members | Done
2 | Selection Of the Topic | 2021-02-15 | 2021-02-25 | All the Team Members | Done
3 | Discussion on the Topic | 2021-02-26 | 2021-03-05 | All the Team Members | Done
4 | Topic Finalized | 2021-03-05 | 2021-03-12 | All the Team Members | Done
5 | Selection Of the Project Base(i.e Website or Application). | 2021-03-12 | 2021-03-19 | All the Team Members | Done
6 | Flowchart Designing | 2021-03-19 | 2021-03-25 | All the Team Members | Done
7 | Algorithm Designing | 2021-03-26 | 2021-04-02 | All the Team Members | Done
8 | IDE Selection | 2021-04-02 | 2021-04-09 | All the Team Members | Done
9 | What Theme to use in project(i.e Colour Combination). | 2021-04-09 | 2021-04-11 | All the Team Members | Done
10 | Started Developing | 2021-04-16 | 2021-04-23 | All the Team Members | Done
11 | Discussed Some issues that raised. | 2021-04-23 | 2021-04-26 | All the Team Members | Done
12 | Database Selection | 2021-04-26 | 2021-04-30 | All the Team Members | Done
13 | Discussed Some issues that raised. | 2021-05-01 | 2021-05-05 | All the Team Members | Done
14 | Finished With the Development part | 2021-05-07 | 2021-05-10 | All the Team Members | Done
15 | Discussion For the Documentation | 2021-05-10 | 2021-05-12 | All the Team Members | Done
16 | Started Documentation | 2021-05-12 | 2021-05-20 | All the Team Members | Done
17 | Started Presentation Work | 2021-05-20 | 2021-05-25 | All the Team Members | Done
18 | Gave a small Presentation to the guide. | 2021-05-25 | 2021-05-29 | All the Team Members | Done
19 | Project Submitted | 2021-06-11 | 2021-06-11 | All the Team Members | Done